}

Guide 1. APT Project Definition

Capstone Course

- PART I

1. Personal Information

Complete the following table with the requested information.

| Student name | Omar Mejía Tomás Benjamín Suárez Alvarado Esteban Cabeza Escobar Jorge Soto |
| --- | --- |
| Chilean ID (RUT) | 26.188.028-8 21.413.425-K 20.000.416-7 21.300.436-0 |
| Program | Information Technology Engineering |
| Campus | Padre Alonso Ovalle (P.A.O) |

2. APT Project Description

In this section, briefly state the name of your APT project and the graduate profile competencies you will apply. If your program defines professional areas, also mention the areas related to the project.

| Project name | EduGestor |
| --- | --- |
| Professional area(s) | Software development · IT project management · Data modeling and administration. |
| Competencies | Perform certification and validation tests for products and processes using industry best practices. Manage IT projects and provide alternatives for decision-making according to organizational requirements. Build data models that support organizational requirements with a defined design that can scale over time. Develop a software solution using techniques that organize the development and maintenance process and help achieve the project objectives. |

3. APT Project Rationale

Complete the following fields with the requested information. This section asks you to describe the project in detail and explain its relevance and connection with your professional field.

| Relevance of the APT Project | Rural schools in Chile often work with limited technology and many manual administrative processes. Academic information can be spread across spreadsheets, paper documents, and teachers’ personal files. This makes it difficult to keep information updated, access it quickly, and identify who entered each record. Rural schools may also have multigrade classrooms, where one teacher works with several grade levels and subjects. As a result, teachers may need to prepare and review many assessments with limited available time. The project addresses two main problems: academic information is dispersed and difficult to trace, and a small teaching staff has a high administrative and teaching-preparation workload. This situation is common in rural Chilean schools with small communities, unstable internet connections, and management teams that may also work as teachers. It affects four groups: school managers, who need consolidated information for decisions; teachers, who spend time on administrative work instead of teaching; students, whose academic progress depends on dispersed records; and parents or guardians, who may not have a clear channel to follow student progress. The project provides three main benefits. First, it centralizes information in one platform with role-based access and record traceability. Second, it reduces the time teachers spend on administrative tasks and assessment creation through AI assistants designed for specific tasks. Third, the multi-institution architecture allows different schools to use the same platform without sharing their data. This can make the solution more affordable for small schools. For the Information Technology field, the project involves three common industry challenges: designing a multi-tenant architecture with verifiable data isolation, integrating language models into a business application with access control, and handling sensitive personal data under Chilean regulations. These skills can be applied to many SaaS products. |
| --- | --- |
| APT Project Description | The goal of the project is to transform EduGestor, currently a monolithic application for one school, into a multi-institution platform with AI assistants that support academic management. The development has three connected areas. The first is the redesign of the data model. A new Institution entity is added, and global uniqueness rules are reviewed so they can include the institution identifier. This solves a real case in Chile: the same person, such as a parent with children in two schools or a teacher working in both, can correctly exist in more than one institution. The second area is the access mechanism. Django authentication is kept, and the institution is added as a scope instead of replacing authentication. Each user enters through the address of their school, and the system identifies the institution before any database query is made. The third area is the AI layer, built with Gemini Enterprise Agent Platform and its agent development kit. Three assistants are planned with separate scopes. The first creates draft assessments aligned with the national Learning Objectives, which the teacher reviews and approves before use. The second creates summaries of grades and attendance; the numbers come from database queries and the model only writes the explanation. The third is a system-use copilot based on the EduGestor manual. None of the assistants has direct database access. They use an internal set of limited functions that checks the institution and user role before making a query. |
| Connection of the Project with the Graduate Profile | The project applies the four selected graduate profile competencies in an integrated way. The following points explain how each competency is used during development. - Product and process testing: the team designs and executes a three-level test plan. It includes functional tests for role-based flows, automated isolation tests to confirm that no query returns data from another institution, and quality evaluation of AI outputs based on how much content the teacher must correct before approval. - IT project management and alternatives: the project requires decisions between architecture options with different costs, risks, and maintenance needs. Examples include multi-tenant strategies, authentication mechanisms, and the order of database migrations. Each decision is documented with the options reviewed and the criteria used. - Building scalable data models: this is a central competency in the project. The current model, with thirteen entities, must evolve into a multi-institution schema without losing data or referential integrity. New entities are also required to store assessment instruments. Scalability must be verifiable because the same schema should support one school or several schools. - Developing a software solution with an organized development and maintenance process: this is applied through version control, versioned database migrations, a reproducible procedure for generating test data, and the integration of an external component without changing the existing business logic. |
| Connection with Professional Interests | The team is mainly interested in backend software development and data modeling, with a growing interest in using artificial intelligence to solve real problems. The project reflects this interest because most of the work is not focused on the interface. It is focused on the data model, the access layer, and the controlled integration of a language model into an existing application. The team is also interested in SaaS product development. SaaS applications have specific challenges such as customer data isolation, customer-specific configuration, and usage-based operating costs. Solving these challenges in an academic project provides useful experience without putting real production data at risk. The education context is also important to the team. Working with rural schools means that technical decisions must consider limited connectivity, small budgets, and users with different levels of digital experience. The project helps the team develop three relevant professional skills: multi-tenant application architecture, responsible AI integration, and personal data handling according to current regulations. |
| Feasibility of the APT Project | The project is feasible within the semester because it does not start from zero. There is already a working application with thirteen modeled entities, four user profiles, a repository with commit history, and previous documentation, including a technical report and a user manual. The semester work extends this existing base instead of building the complete system again, which reduces the project risk. - Semester duration: 10 weeks divided into three phases. The work plan is organized in stages, and each stage produces an independent result that can be demonstrated. If the schedule becomes limited, the last and least critical activity can be reduced without affecting previous components. - Assigned class hours: the work is distributed among the team members according to the responsibilities defined in the work plan. This allows different project areas to progress in parallel during the available hours. - Required resources: all main tools are free to use, including Python, Django, PostgreSQL in a local container, Git, GitHub, the open-source agent development kit, and the free tier of the language-model API. The team does not need special hardware or paid services to complete the planned scope. - External factors that support development: the base system is already built, functional, and previously reviewed with the teacher; previous documentation is available and can also be used as a knowledge source for one assistant; the team already knows the technology stack; and free service tiers allow development and demonstration without additional cost. - External factors that may make development difficult and how they are managed: (1) The complete scope is large for one semester, so cloud deployment is placed at the end and is optional. If there is not enough time, the production architecture will be documented instead. (2) Access to a paid cloud account is uncertain, so development can be completed locally using free API access. (3) The system works with information related to minors, so only synthetic test data will be used during development. No real student data will be sent to the system or external APIs. (4) A poorly filtered query could expose data between institutions, so data isolation is implemented as a structural rule and checked with automated tests. (5) Team coordination is managed with feature branches, clear module responsibilities, and cross-review before code is merged. |

- PART II

4. Objectives

In this section, define the general and specific objectives of the APT Project. The objectives should be clear, concise, and easy to understand. It is recommended to start them with an action verb.

| General objective | Develop a multi-institution web platform for centralized school management that includes AI assistants to support teachers and academic information queries, while ensuring verifiable data isolation for each institution. |
| --- | --- |
| Specific objectives | - Redesign the data model to support multiple institutions using a logical multi-tenant structure and update the integrity rules that currently work at a global level. - Migrate the database engine to PostgreSQL and create a reproducible process for generating synthetic test data. - Implement authentication and institution-based routing while keeping the existing authentication system. - Build an internal domain interface that exposes academic queries as limited functions controlled by user role and institution. - Develop an AI assistant that generates assessment drafts based on national Learning Objectives, with mandatory teacher review and approval. - Develop an assistant for grade and attendance summaries, and a system-use copilot based on the project documentation. - Design and apply a test plan to validate role-based functionality, data isolation between institutions, and the quality of AI assistant outputs. - Document the architecture, the design alternatives evaluated, and the development evidence of the project. |

5. Methodology

In this section, describe the methodology you will use to develop the APT project, including the main stages and work methods.

Methodology Description

The project uses an agile and incremental methodology, which was also used in previous stages of EduGestor. The work is divided into functional increments, and each increment produces an independent result that can be demonstrated and tested. This approach allows the team to show partial progress during reviews with the teacher and reduces the impact of delays on the complete project. Each increment follows four steps: requirement analysis and evaluation of alternatives when necessary; solution design and documentation of the selected decision; implementation; and validation through testing before the result is merged into the main repository branch. The decision record is part of the development cycle and provides evidence of IT project management skills. The project has five main stages: analysis of the required expansion; design of the target architecture and evaluation of alternatives; development and migration of the multi-institution data model; development of the AI assistant layer; and final validation, documentation, and presentation preparation. The schedule is shown in the Gantt chart in section 8. Team Functions, Tasks, and Responsibilities Each team member is responsible for a different project area. The four graduate profile competencies are also supported by shared testing and documentation activities. Omar Mejía — Project leader and data architecture. Responsible for coordinating the work plan and tracking progress. Designs the multi-institution data model, defines integrity rules, creates migrations, and manages the migration to PostgreSQL. Also develops the synthetic data generation command. He leads this area because he has continuity from the previous version and knows the current data model. Thomas — Backend development and access layer. Responsible for authentication, institution-based routing, middleware for institution resolution, and default data-access filtering. Also builds the internal domain interface and the limited functions used by the assistants. Esteban — Artificial intelligence integration. Implements the three assistants using the agent development kit, indexes document sources, defines the tool contract and model security restrictions, and evaluates the quality of generated outputs. Jorge Soto — Quality, validation, and documentation. Designs the three-level test plan: role-based functional testing, institution-isolation testing, and quality evaluation of assistant outputs. Defines acceptance criteria before implementation and coordinates the technical report and user manual. Whole team — Cross-review of code before merging into the main branch and execution of tests on each module before delivery.

6. Evidence

Describe the evidence that will be evaluated in the progress report and the final APT project report. The evidence should be agreed with the teacher and should show or document how the work was implemented.

| Evidence type (progress or final) | Evidence name | Description | Justification |
| --- | --- | --- | --- |
| Progress | Architecture and design decisions document | Record of the architecture alternatives reviewed, the decision criteria used, and the selected target architecture, including diagrams. | Direct evidence of project management competency because it shows that different alternatives were considered for decision-making. |
| Progress | Multi-institution data model | Updated entity-relationship diagram and executed migration files, including composite uniqueness rules. | Evidence of the design and implementation of a data model that can scale over time. |
| Progress | Functional multi-institution module prototype | Working application with three test institutions, differentiated access by school, and functional role-based panels. | Shows the construction of the software solution based on the designed data model. |
| Progress | Test plan | Design of functional test cases, institution-isolation tests, and assistant-output evaluation tests with acceptance criteria. | Evidence of product and process validation test design using good practices. |
| Final | System with the three assistants integrated | Complete application with the assessment generator, summary assistant, and system-use copilot working through the internal domain interface. | Evidence of the integration of the different software solution components. |
| Final | Test execution and applied improvements report | Results of the test plan, detected defects, and improvements added to the product based on those results. | Evidence that tests were applied and improvements were developed from the results. |
| Final | AI quality evaluation record | Measurement of the percentage of generated content that the teacher must correct before approving an assessment, compared with the previously defined acceptance criterion. | Provides evidence that the assistant meets its purpose instead of only stating that it works. |
| Final | Repository with version history | Git repository with commit history, feature branches, and records of merges into the main branch. | Evidence of project control and an organized development and maintenance process. |
| Final | Final technical report and updated user manual | Complete project documentation including decisions, results, and system operation guidance for each user profile. | Meets the presentation standards required by the discipline and supports future maintenance. |

7. Work Plan

Use the following table to define the APT Project work plan.

| APT Project Work Plan |  |  |  |  |  |  |
| --- | --- | --- | --- | --- | --- | --- |
| Competency or competency units | Activity/Task name | Activity/Task description | Resources | Activity duration | Responsible person | Notes |
| Manage IT projects | APT project definition | Definition guide, objectives, scope, and work plan. Agreement on evidence with the teacher. | APT guide, previous documentation | 2 weeks | Whole team | Facilitator: the report and manual already exist. Challenge: agreeing on the final scope. |
| Manage IT projects | Architecture analysis and design | Evaluation of multi-tenant architecture and authentication alternatives. Definition of the target architecture. | Technical documentation, diagrams | 2 weeks | Omar Mejía | The documented evaluation of alternatives is the main evidence for this competency. |
| Build data models | Database engine migration and test data | Change from SQLite to local PostgreSQL and create a synthetic-data generation command for three institutions. | PostgreSQL, Docker, Django | 2 weeks | Omar Mejía | This is done before the schema change to avoid debugging the migration twice. |
| Build data models | Multi-institution data model | Institution entity, three-step migrations, and conversion of global uniqueness rules into composite rules. | Django, PostgreSQL | 3 weeks | Omar Mejía | Challenge: a poorly defined rule may not protect the data and may not generate an error. This is reduced through isolation tests. |
| Develop software solution | Institution-based authentication | Authentication backend, institution-resolution middleware, and default filtering for data access. | Django | 2 weeks | Thomas | Facilitator: the existing authentication system is kept without major changes. |
| Develop software solution | Internal domain interface | Limited academic-query functions with unit tests before AI integration. | Django, testing framework | 2 weeks | Thomas | Because the functions are tested first, later assistant integration is more direct. |
| Develop software solution | Application-use copilot | Index the user manual and implement the first assistant. | Agent development kit, model API | 1 week | Esteban | It is built first because it is the simplest assistant and does not use personal data. |
| Develop software solution | Assessment generator | Entities for questions and answer options, curriculum indexing, draft generation, and teacher editing. | Agent development kit, curriculum documents | 3 weeks | Esteban | Challenge: using the complete curriculum is not feasible, so the scope is limited to one subject and two grade levels. |
| Develop software solution | Academic summary assistant | Query grades and attendance through the internal interface, with values calculated by database queries. | Agent development kit, model API | 2 weeks | Esteban | Reuses the functions already developed in the internal interface. |
| Perform certification tests | Test plan execution and improvements | Functional, isolation, and AI-output quality tests. Defect correction. | Testing framework, synthetic data | 2 weeks | Jorge Soto | The improvements made from test results provide evidence for the third indicator of this competency. |
| Manage IT projects | Documentation, final report, and presentation | Final technical report, updated manual, and preparation of the demonstration. | Word processor, repository | 3 weeks | Whole team | Dedicated time is reserved because late documentation can cause incomplete deliveries. |
| Develop software solution | Cloud deployment (optional) | Environment configuration, application container, and deployment with a managed database. | Cloud account with billing | 2 weeks | Whole team | This is the only optional activity. If it is not executed, the deployment architecture will be documented. |

8. Gantt Chart

Use a Gantt chart format to organize the activities from the previous section according to the academic period. The schedule should include the three phases of the Capstone course.

| Activity | Phase 1 |  |  |  | Phase 2 |  |  |  |  |  |  |  |  |  |  |  | Phase 3 |  |  |  |
| --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- | --- |
|  | W 1 | W 2 | W 3 | W 4 | W 5 | W 6 | W 7 | W 8 | W 9 | W 10 | W 11 | W 12 | W 13 | W 14 | W 15 | W 16 |  | W 17 | W 18 |
| APT project definition |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Architecture analysis and design |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Database engine migration and test data |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Multi-institution data model |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Institution authentication and routing |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Internal domain interface |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Application-use copilot |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Assessment generator |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Academic summary assistant |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Test plan execution and improvements |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Documentation, final report, and presentation |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |
| Cloud deployment (optional) |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |  |

9. Compliance with Disciplinary Quality Indicators

Mapping of the project design to the quality indicators related to the selected graduate profile competencies, showing where each indicator is demonstrated.

1.1 — Designs product and process validation tests using industry best practices. A three-level test plan is defined: role-based functional tests, automated isolation tests between institutions, and previously defined acceptance criteria for assistant outputs.

1.2 — Applies product and process validation tests using industry best practices. The test plan is executed with synthetic data from three institutions, and the results are documented in the test execution report.

1.3 — Develops product improvements based on test results. Detected defects are corrected, and the applied improvements are recorded with traceability to the related commit. The project already has experience with this improvement cycle from previous stages.

2.1 — Plans IT projects and provides alternatives for decision-making. Evidence includes the work plan and Gantt chart in sections 7 and 8, and an architecture document with alternatives for the multi-tenant strategy, authentication mechanism, and migration order, each with clear decision criteria.

2.2 — Controls IT projects and provides alternatives for decision-making. The team uses version control with feature branches and cross-review, tracks progress against the Gantt chart, and defines in advance which activities can be removed if the schedule becomes limited.

3.1 — Designs scalable data models to support organizational requirements. Evidence includes a multi-institution entity-relationship diagram with composite uniqueness rules and new entities required to store assessment instruments.

3.2 — Implements scalable data models to support organizational requirements. Evidence includes versioned migrations executed on PostgreSQL, a reproducible data-generation command, and an automated test that verifies that all relevant models include their institution.

4.1 — Builds a software solution with an organized development and maintenance process. The Django application is structured with models, views, forms, routes, and templates, using incremental development, version control, and a reproducible environment.

4.2 — Integrates different components of a software solution. The agent layer is integrated with the existing application through an internal domain interface, without direct database access from the external component.

4.3 — Deploys a software solution using an organized development and maintenance process. The project includes environment-based configuration, an application container, and a documented deployment procedure. Cloud execution depends on the availability of a billing-enabled account.

10. Abstract

Project summary. This version is written in intermediate English using clear Information Technology terminology.

EduGestor is a web-based school management system developed with Django. It centralizes academic and administrative information for a rural school and provides different access according to user roles: administrator, teacher, student, and parent or guardian. The system is already operational and covers the main academic cycle, including enrollment, academic records, assessments, grades, and attendance.

This APT Project proposes the evolution of the current system into a multi-institution SaaS platform. The new platform will support several schools from one application while keeping each institution’s data isolated. It will also include a layer of generative AI assistants using Gemini Enterprise Agent Platform.

The proposal includes three assistants with different scopes and risk levels. The first is an assessment generator based on the national Learning Objectives and does not process personal data. The second is an assistant for grades and attendance; its numerical results always come from verified queries and not from the AI model. The third is a system-use copilot based on the application manual. The model can only use a limited set of approved tools. This design reduces the risk of SQL injection and prevents a malicious prompt from increasing a user’s permissions.

The project integrates four graduate profile competencies: designing and implementing a scalable data model, building and integrating software components, planning and controlling the project with documented architecture decisions, and designing and applying validation tests for the product and its processes.

11. Conclusions

Individual conclusions from each team member about the project definition phase.

Omar Mejía. My main learning in this phase was understanding that supporting several institutions is not only about adding one new table. It requires reviewing every data integrity rule that currently works at a global level. Identifying the real scope before writing code helped us avoid underestimating the work. It also helped us plan the database engine migration before changing the data schema, which is a safer and more organized approach.

Thomas. Defining the project helped me separate two concepts that are often confused: authentication, which identifies who the user is, and scope, which defines the institution the user belongs to. Understanding this difference allowed us to keep the existing authentication system and solve the requirement with less code than we first expected.

Esteban. The definition phase showed me that AI should be selected because of the problem it solves, not only because the technology is new. We decided to create three assistants with different data, risks, and permissions instead of one assistant with access to everything. This is both a design decision and a security measure because a component cannot use a tool that is not available to it.

Jorge Soto. Defining the project made me think about how quality should be measured before development starts. For the assessment generator, we needed a clear way to know if the tool is useful. We decided to measure the percentage of generated content that a teacher must correct before approval. Without this criterion, we could only say that the tool works, but we could not demonstrate its quality with evidence.

12. Reflection

Team reflection on the APT Project definition process.

The definition of this APT Project showed us that one of the most difficult parts of a software project is defining a realistic scope. At first, the team wanted to include multi-institution support, artificial intelligence, database migration, and cloud deployment at the same level. After analyzing the project, we understood that trying to complete everything with the same priority could result in an incomplete delivery. Organizing the work by dependencies and identifying the optional activity was more useful than increasing the scope.

A second reflection is about documentation. In previous stages, the team saw documentation as a task to complete after development. In this project, documentation has a more important role. The record of evaluated alternatives and decision criteria provides evidence of project management competency. In addition, the user manual becomes the knowledge source for one of the AI assistants. For this reason, documentation becomes part of the product instead of only an academic requirement.

Finally, adding artificial intelligence to a system that manages information related to minors created an important discussion for the team. We decided to work only with synthetic data and to prevent the AI model from accessing the database directly. This was not only a course requirement; it was a professional responsibility. In a real system, technical decisions can affect real people. This is an important difference between completing an academic exercise and developing a real software product.

13. Bibliography and Sources

Sources used for the project definition.

- Google Cloud. Gemini Enterprise Agent Platform (previously Vertex AI). Official product documentation.

- Django Software Foundation. Django documentation: models, migrations and authentication.

- Ministry of Education of Chile. National Curriculum and Learning Objectives.

- Library of the National Congress of Chile. Law 21.719 on personal data protection and processing.

- Previous project documentation: EduGestor Project Report and EduGestor User Manual.

Language note: this document was adapted to intermediate English, with clear grammar and Information Technology vocabulary. Technical terms such as backend, multi-tenant, SaaS, API, middleware, and data model are kept because they are standard terms in the field.

En caso de que el Proyecto APT sea grupal, en esta columna deben indicar el nombre de los responsables de cada tarea o actividad. Esto posteriormente permitirá diferenciar la evaluación por cada integrante.